## Template
Takami webshop |  |  | Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4 |  |  | Sprint 5
Start Date: 31/08/2020 |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
ANALYSIS |  | 3 w
Gantt chart | Developer | 1w
Brainstorming | Developer | 3w
Project Plan | Developer | 2w
DESIGN |  | 3 w
Requirements gathering | Developer | 2w
Use cases | Developer | 3w
Wireframes | Developer | 1w
Agreements with client | Developer | 2w
DEVELOPMENT |  | 9 w
UML Diagrams | Developer | 2w
Website | Developer
API connection | Developer | 5w
Interface Design | Developer | 7w
Functionality
Add, delete, udate product | Developer | 3w
Making an order | Developer | 2w
Process Report D | Developer | 2 d
TESTING |  | 3w
Test plan D | Developer | 1w
Test report D | Developer | 1w
Improving solution | Developer | 1w
PRESENTATION |  | 3w
Finish the solution D | Developer | 3w
Powerpoint presentation D | Developer | 2d
Deliverable |  | D

## Month 1
A
| Project Title... |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
| Start Date: |  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
| DEVELOPMENT |  | 5 d
| Finalize Script | owner | 2 d
| Attachments | owner | 3 d
| Financing | owner
| PRE-PRODUCTION |  | x d
| Casting | owner
| Set Design | owner
| Locations | owner
| Costumes | owner
| Hair | owner
| Make-up | owner
| PRODUCTION |  | x d
| Rehearsals | owner
| Principal Photography | owner
| Second Unit | owner
| POST-PRODUCTION |  | x d
| Editing | owner
| VFX | owner
| Scoring | owner
| Sound Editing | owner
| Color Grading | owner
| DISTRIBUTION |  | x d
| Distribution Deals | owner
| Marketing Push | owner
| Press Tour | owner
| Premieres | owner
| ANNOTATIONS |  |  | WEEK 4 TH: Blocked out event
Blocked out phase
[27 empty] | N | Dependency
[27 empty] | n | Dependent Event
| #NAME? |  | Modern Production Management Software. Create production calendars, breakdowns, call sheets & more on studiobinder.com | WEEK 4 T: © 2017 - StudioBinder